# Chapter 3 — §3.4 Scrum Artifacts (Complete)

System: Barangay Culiat Public Facilities Reservation System (CPRF)
Authors: Joricho E. Azuela, Luis Miguel N. Follero, Hajar P. Gili, Daryll Parcia, Gilbert A. Tablac Jr.
Institution: Bestlink College of the Philippines — BS Information Technology
Last updated: July 2026
Status rule: Items reflect implemented behavior unless marked Planned or Partial.

How to use in Word: Copy each section and table into CHAPTER-3-RESEARCH-2.docx under §3.4 Scrum Artifacts, replacing placeholder rows. Renumber figures/tables to match your thesis. Cross-reference: docs/USER_STORIES_AND_BACKLOG_COMPLETE.md, docs/MODULES_LIST.md.

## 3.4 Scrum Artifacts

Scrum artifacts used in this capstone include the Product Backlog (functional and non-functional requirements), specialized Enterprise Information System (EIS) backlogs for security, standards, integration, and analytics, the Sprint Backlog with task breakdown, burndown tracking, and the Increment record of working software delivered each sprint. All items were prioritized by the Product Owner and validated against the production codebase at cprf.infragovservices.com.

Definition of Done (DoD) — applied to every increment: 1. Code merged to the main branch and routed in index.php 2. Role permissions declared in config/permissions.php 3. Manual smoke test passed (see docs/DEPLOYMENT_SMOKE_TESTS.md) 4. Related documentation updated in docs/ 5. No critical security regressions (CSRF, auth, document access)

## 3.4.1 Product Backlog (User Stories)

The Product Backlog is the master list of features for the AI-Driven Facilities Reservation System with Predictive Scheduling Features for Barangay Culiat. Items are grouped into four modules (ten features each). Priority: 1 = highest, 3 = lower. Status reflects July 2026 implementation.

Table 3. Product Backlog (User Stories)

| User Story No. | Features / Task | User Stories | Priority | Status |
| --- | --- | --- | --- | --- |
| MODULE 1 — Authentication & User Management |  |  |  |  |
| F1 | Resident registration | As a resident, I can register with Barangay Culiat street address, contact details, and optional Valid ID so only eligible residents sign up. | 1 | Done |
| F2 | Email verification | As a resident, I must verify my email before full system access. | 1 | Done |
| F3 | Login with OTP | As a resident, I log in with email/password and complete email OTP verification. | 1 | Done |
| F4 | TOTP (Google Authenticator) | As a resident, I can enable TOTP for stronger login security and recover via email if device is lost. | 2 | Done |
| F5 | Password reset | As a user, I can reset my password through a secure emailed token. | 1 | Done |
| F6 | Session & abuse controls | As the system, I enforce CSRF protection, session timeout, login lockout, and registration rate limits. | 1 | Done |
| F7 | Profile management | As a resident, I can update profile, address, geocoordinates, photo, and notification preferences. | 2 | Done |
| F8 | User directory & approval | As staff/admin, I can search users and approve, deny, lock, or unlock accounts. | 1 | Done |
| F9 | ID verification queue | As staff/admin, I can verify uploaded Valid IDs from a dedicated queue tab. | 1 | Done |
| F10 | Data Privacy export | As a resident, I can export my personal data (RA 10173 JSON export). | 2 | Done |
| MODULE 2 — Public Portal & Facility Management |  |  |  |  |
| F11 | Public home page | As a visitor, I can view featured facilities and latest announcements on the landing page. | 1 | Done |
| F12 | Facilities listing | As a visitor, I can browse public facility listings with images. | 1 | Done |
| F13 | Facility details | As a visitor, I can view facility specs, hours, and calendar snapshot. | 1 | Done |
| F14 | Facility CRUD | As staff/admin, I can create, edit, and manage facility records. | 1 | Done |
| F15 | Images & citations | As staff/admin, I can upload facility images with attribution/citation. | 2 | Done |
| F16 | Hours & geocoding | As staff/admin, I can set operating hours and geocode facility location. | 2 | Done |
| F17 | Blackout dates | As staff/admin, I can block dates (single or range) to prevent bookings. | 1 | Done |
| F18 | Facility QR poster | As staff/admin, I can generate and print facility check-in QR posters. | 2 | Done |
| F19 | Announcements archive | As a visitor, I can read public announcements with search and categories. | 2 | Done |
| F20 | Contact inquiries | As a visitor, I can submit a contact form; staff manage inquiries in admin inbox. | 2 | Done |
| MODULE 3 — Booking & Reservations |  |  |  |  |
| F21 | Book a facility | As a resident, I can submit a reservation (date, time, purpose, attendees, documents). | 1 | Done |
| F22 | AI conflict detection | As a resident, I see real-time conflict warnings and alternative time slots. | 1 | Done |
| F23 | AI recommendations | As a resident, I receive facility recommendations with distance and purpose scoring. | 1 | Done |
| F24 | Auto-approval engine | As the system, I auto-approve bookings when all eight rule checks pass. | 1 | Done |
| F25 | Approval queue tabs | As staff/admin, I manage pending and approved reservations in separate tabs with filters. | 1 | Done |
| F26 | Staff decisions | As staff/admin, I can approve, deny, postpone, hold, modify, or cancel with reasons. | 1 | Done |
| F27 | My Reservations | As a resident, I view my bookings in calendar and list views. | 1 | Done |
| F28 | Reschedule / cancel | As a resident, I can reschedule or cancel per system rules (advance notice, limits). | 2 | Done |
| F29 | Walk-in booking | As staff, I can book on behalf of a resident at the barangay desk. | 2 | Done |
| F30 | Booking limits | As the system, I enforce ≤3 active/30 days, ≤60-day advance, ≤1 booking/day. | 1 | Done |
| MODULE 4 — AI, Attendance, Reports, Integrations & Admin |  |  |  |  |
| F31 | Manual check-in/out | As a user, I can manually check in and out with optional photo proof. | 1 | Done |
| F32 | QR check-in/out | As a user, I can scan the facility QR to check in/out for today’s approved booking. | 1 | Done |
| F33 | Occupancy monitor | As staff, I see live occupancy status and can apply overrides. | 2 | Done |
| F34 | Smart Scheduler & chatbot | As a user, I use the Smart Scheduler and Gemini AI assistant (with ML fallback). | 1 | Done |
| F35 | Calendar & iCal | As a user, I view month/week/day calendar and export to iCal. | 2 | Done |
| F36 | Reports & export | As staff/admin, I view KPI charts and export CSV/PDF reports. | 1 | Done |
| F37 | CIMM maintenance sync | As staff, I sync CIMM schedules to facility status/blackouts; system auto-announces. | 1 | Done* |
| F38 | Integration dashboards | As staff, I view Infrastructure (Brgy Culiat) and UMAN utility integration pages. | 2 | Done* |
| F39 | Audit & documents | As admin, I manage audit trail, document retention, and archival cron. | 1 | Done |
| F40 | Notifications | As a user, I receive in-app, email, and SMS (opt-in) notifications on key events. | 1 | Done |

* Requires API keys and/or cron on production (CIMM_API_KEY, UMAN_API_KEY).

Future backlog (not in Table 3): Filipino/Tagalog UI, PWA, bulk CSV user import, staff daily digest email, infrastructure auto-blackout — see docs/USER_STORIES_AND_BACKLOG_COMPLETE.md Part B.3.

## 3.4.2 Product Backlog for EIS Information Security

Security requirements align with LGU information-system standards, the Data Privacy Act (RA 10173), and OWASP-oriented web application practices implemented in CPRF.

Table 4. Product Backlog for EIS Information Security

| EIS No. | EIS User Stories | EIS IS Priority | Revision Priority | Status |
| --- | --- | --- | --- | --- |
| IS-1 | As the system, I hash passwords with bcrypt and enforce password complexity on registration and reset. | 1 | 1 | Done |
| IS-2 | As the system, I validate CSRF tokens on all state-changing forms and API actions. | 1 | 1 | Done |
| IS-3 | As the system, I rate-limit login and registration attempts and lock accounts after repeated failures. | 1 | 1 | Done |
| IS-4 | As a user, I complete email OTP on login; I may enable TOTP (Google Authenticator) with email recovery. | 1 | 2 | Done |
| IS-5 | As the system, I present Cloudflare Turnstile captcha on registration when enabled. | 2 | 2 | Done |
| IS-6 | As the system, I store uploaded IDs and permits outside web root with role-based download access. | 1 | 1 | Done |
| IS-7 | As admin, I can query audit logs for user, reservation, and configuration actions. | 1 | 2 | Done |
| IS-8 | As a resident, I can export my personal data; registration requires Terms and Privacy acceptance. | 1 | 2 | Done |
| IS-9 | As the system, I regenerate session IDs, enforce timeout, and use secure cookie flags. | 1 | 1 | Done |
| IS-10 | As admin, I can lock users with documented reason and email notification. | 2 | 3 | Done |

## 3.4.3 Product Backlog for EIS Standards

Development and architecture standards ensure maintainability, deployability, and alignment with the capstone’s modular monolith design (not containerized microservices).

Table 5. Product Backlog for EIS Standards

| EIS Standard No. | EIS Standard User Stories | EIS Standard Priority | Revision Priority | Status |
| --- | --- | --- | --- | --- |
| STD-1 | As a developer, I follow a single-entry modular monolith routed through index.php with views under resources/views/. | 1 | 1 | Done |
| STD-2 | As a developer, I use MySQL with normalized schema (database/schema.sql) and versioned migrations. | 1 | 1 | Done |
| STD-3 | As the system, I enforce role-based access (Resident, Staff, Admin) via config/permissions.php. | 1 | 1 | Done |
| STD-4 | As a developer, I configure secrets and integrations through .env (never committed). | 1 | 1 | Done |
| STD-5 | As a developer, I run PHPUnit smoke tests in GitHub Actions CI on push. | 2 | 2 | Done |
| STD-6 | As an operator, I run documented cron jobs for reminders, CIMM sync, archival, and auto-decline. | 2 | 2 | Done |

### 3.4.3.1 UI/UX (Icons, Color, etc…)

User interface standards support accessibility, mobile use, and consistent LGU branding across public and dashboard surfaces.

Table 5.1. Product Backlog for EIS Standards — UI/UX

| EIS Standard No. | EIS Standard User Stories | EIS Standard Priority | Revision Priority | Status |
| --- | --- | --- | --- | --- |
| UI-1 | As a user, I can use the system on mobile without horizontal scrolling on core booking flows. | 1 | 1 | Done |
| UI-2 | As a user, I see consistent status badges (pending, approved, denied, maintenance) with semantic colors. | 1 | 1 | Done |
| UI-3 | As a user, I can enable dark mode on dashboard pages. | 2 | 2 | Done |
| UI-4 | As a user, I confirm destructive actions (cancel, delete) through modal dialogs. | 1 | 2 | Done |
| UI-5 | As a user, I receive inline validation messages on forms (registration, booking, profile). | 1 | 1 | Done |
| UI-6 | As a visitor, I see a modern public landing design with high-contrast cards and facility imagery. | 2 | 3 | Done |
| UI-7 | As a user, I navigate grouped sidebar sections with collapsible state persistence. | 2 | 3 | Done |
| UI-8 | As a visitor, I see image citations/attribution on facility photos where required. | 3 | 3 | Done |
| UI-9 | As a user, I use the redesigned Reservations Management page with tabbed pending/approved queues. | 1 | 1 | Done |
| UI-10 | As a resident, I see upcoming CIMM maintenance chips on the booking calendar before maintenance starts. | 2 | 2 | Done |

Not implemented UI standards (future): Filipino/Tagalog language toggle (UI-11, planned); PWA install prompt (UI-12, planned).

## 3.4.4 Product Backlog for EIS Integration

Integration backlog items connect CPRF to Quezon City LGU systems and third-party services. Scope is facilities only; equipment reservation is out of scope.

Table 6. Product Backlog for EIS Integration

| EIS Integration No. | EIS Integration User Stories | EIS Integration Priority | Revision Priority | Status |
| --- | --- | --- | --- | --- |
| INT-1 | As staff, I pull CIMM maintenance schedules, update facility status/blackouts, and postpone conflicts. | 1 | 1 | Done* |
| INT-2 | As staff, I view QC Infrastructure planned construction reports filtered to Barangay Culiat. | 1 | 2 | Connected† |
| INT-3 | As staff, I assign UMAN utility assets to facilities when UMAN API is configured. | 2 | 2 | Done* |
| INT-4 | As the system, I use Google Gemini for chatbot replies and auto-written public maintenance/blackout announcements. | 1 | 1 | Done* |
| INT-5 | As a resident, I can pay via PayMongo when payments are enabled for a facility. | 3 | 3 | Optional‡ |
| INT-6 | As the system, I send transactional email (SMTP) and SMS (opt-in) for OTP, approvals, and reminders. | 1 | 1 | Done |
| INT-7 | As the system, I expose public availability API for guest assistant widget (/api/public/availability). | 2 | 2 | Done |
| INT-8 | As an external system, I POST to unified /api/integrations/* gateway. | 3 | 3 | Not implemented |

* Requires CIMM_API_KEY / UMAN_API_KEY / GEMINI_API_KEY and cron where applicable.
† Connected (thesis): dashboard receives barangay-scoped construction reports; live auto-blackout from infrastructure timelines is not implemented.
‡ PAYMENTS_ENABLED=false by default for capstone (free facility use policy).

## 3.4.5 Product Backlog for Analytics

Analytics backlog covers operational reporting inside CPRF and enterprise-level insights for LGU decision-making.

### 3.4.5.1 Application System Analytics

In-application analytics help staff monitor reservations, occupancy, and facility utilization.

Table 7. Product Backlog for Analytics — Application System Analytics

| ASA No. | EIS Integration User Stories | EIS Integration Priority | Revision Priority | Status |
| --- | --- | --- | --- | --- |
| ASA-1 | As staff/admin, I view dashboard KPI charts with date-range filters. | 1 | 1 | Done |
| ASA-2 | As staff/admin, I generate reservation reports by status, facility, and date range. | 1 | 1 | Done |
| ASA-3 | As staff/admin, I export filtered report data to CSV. | 1 | 2 | Done |
| ASA-4 | As staff/admin, I print or save PDF views of reports. | 2 | 2 | Done |
| ASA-5 | As staff, I monitor live occupancy from check-in state on the occupancy dashboard. | 1 | 1 | Done |
| ASA-6 | As staff/admin, I view calendar aggregates (month/week/day) for booking density. | 2 | 2 | Done |
| ASA-7 | As admin/dev, I use AI Model Lab to test ML models and demo scenarios. | 3 | 3 | Done |
| ASA-8 | As staff, I see full demand-forecasting dashboard in Reports. | 2 | 2 | Partial |

### 3.4.5.2 EIS Analytics

Enterprise analytics support compliance, audit, and cross-system visibility.

Table 8. EIS Analytics

| EIS Analytics No. | EIS Analytics Stories | EIS Analytics Priority | Revision Priority | Status |
| --- | --- | --- | --- | --- |
| EA-1 | As admin, I query and export audit trail to PDF for compliance reviews. | 1 | 1 | Done |
| EA-2 | As staff/admin, I view per-user violation history for governance decisions. | 1 | 2 | Done |
| EA-3 | As staff, I infer facility utilization trends from reservation and check-in data. | 2 | 2 | Done |
| EA-4 | As admin, I view integration health and sync status on system settings pages. | 2 | 2 | Done |
| EA-5 | As staff, I track CIMM sync statistics (last run, records updated) on maintenance page. | 2 | 2 | Done |
| EA-6 | As admin, I use unified health-check endpoint (DB, mail, ML, CIMM). | 3 | 3 | Not implemented |

## 3.4.6 Sprint Backlog (User Stories)

Work was organized in weekly sprints (Agile Scrum) from November 2025 through July 2026. Each sprint task maps to Product Backlog or EIS items. Task phases: PLANNING → DESIGN → CODE → DOCUMENTATION.

Table 9. Sprint Backlog (User Stories)

| Task No. | User Story No. | User Stories | Tasks | Timeline | Responsible Team Member/s |
| --- | --- | --- | --- | --- | --- |
| SPRINT 1 — Dec 12–Dec 25, 2025 · Authentication & Security Foundation |  |  |  |  |  |
| S1_1 | IS-1, IS-3, F6 | Enforce password policy, login lockout, and registration rate limits | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 12–18 | L. Follero, G. Tablac Jr. |
| S1_2 | F1, F2 | Resident registration with Barangay Culiat address and email verification | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 12–18 | L. Follero |
| S1_3 | F3, IS-4 | Email OTP login flow and OTP email templates | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 12–18 | L. Follero, G. Tablac Jr. |
| S1_4 | F5 | Forgot/reset password with secure token emails | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 19–25 | G. Tablac Jr. |
| S1_5 | IS-2, IS-9 | CSRF protection, session timeout, secure cookies | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 19–25 | L. Follero |
| SPRINT 2 — Dec 26, 2025–Jan 8, 2026 · Profile, Documents & Facilities |  |  |  |  |  |
| S2_1 | F7, IS-6 | Profile geocoding, document upload validation, secure storage | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 26–Jan 1 | L. Follero, G. Tablac Jr. |
| S2_2 | F8, F9 | User management directory, approval workflow, ID verification tab | PLANNING · DESIGN · CODE · DOCUMENTATION | Dec 26–Jan 1 | L. Follero |
| S2_3 | F11–F13 | Public home, facilities listing, facility details pages | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 2–8 | G. Tablac Jr., H. Gili |
| S2_4 | F14–F16 | Facility CRUD, images, hours, geocoding | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 2–8 | L. Follero |
| S2_5 | UI-1, UI-6 | Responsive public UI polish and landing design | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 2–8 | G. Tablac Jr., D. Parcia |
| SPRINT 3 — Jan 9–Jan 22, 2026 · Booking, AI & Approvals |  |  |  |  |  |
| S3_1 | F21, F30 | Core booking form, limits, and validation rules | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 9–14 | L. Follero |
| S3_2 | F22, F23 | AI conflict detection and facility recommendations APIs | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 9–14 | L. Follero, J. Azuela |
| S3_3 | F24 | Eight-condition auto-approval engine | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 9–14 | L. Follero |
| S3_4 | F25, F26 | Staff approval queue, pending/approved tabs, decision actions | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 15–22 | L. Follero, G. Tablac Jr. |
| S3_5 | F27, F28 | My Reservations, reschedule, cancel flows | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 15–22 | G. Tablac Jr. |
| SPRINT 4 — Jan 23–Feb 28, 2026 · Attendance, Calendar & Reports |  |  |  |  |  |
| S4_1 | F31, F32 | Manual and QR facility check-in/out | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 23–31 | L. Follero |
| S4_2 | F33 | Live occupancy monitor and no-show processing | PLANNING · DESIGN · CODE · DOCUMENTATION | Jan 23–31 | G. Tablac Jr. |
| S4_3 | F35 | Calendar views and iCal export | PLANNING · DESIGN · CODE · DOCUMENTATION | Feb 1–14 | G. Tablac Jr. |
| S4_4 | F36, ASA-1–ASA-4 | Reports page, KPI filters, CSV/PDF export | PLANNING · DESIGN · CODE · DOCUMENTATION | Feb 1–14 | L. Follero, D. Parcia |
| S4_5 | F34 | Smart Scheduler page and Python ML service integration | PLANNING · DESIGN · CODE · DOCUMENTATION | Feb 15–28 | L. Follero, J. Azuela |
| SPRINT 5 — Mar–Jul 2026 · Integrations, Compliance & Polish |  |  |  |  |  |
| S5_1 | INT-1, F37 | CIMM sync, blackout dates, Gemini auto-announcements | PLANNING · DESIGN · CODE · DOCUMENTATION | Mar–Apr | L. Follero |
| S5_2 | INT-4 | Gemini chatbot with ML/rules fallback and booking prefill | PLANNING · DESIGN · CODE · DOCUMENTATION | Apr–May | L. Follero |
| S5_3 | F39, EA-1 | Audit trail, document archival cron, DPA export (F10) | PLANNING · DESIGN · CODE · DOCUMENTATION | May | G. Tablac Jr., H. Gili |
| S5_4 | INT-2, INT-3, F38 | Infrastructure and UMAN integration dashboards | PLANNING · DESIGN · CODE · DOCUMENTATION | May–Jun | J. Azuela, D. Parcia |
| S5_5 | UI-9, UI-10, F17 | Reservations UI redesign, blackout announcements, maintenance calendar chips | PLANNING · DESIGN · CODE · DOCUMENTATION | Jun–Jul | L. Follero, G. Tablac Jr. |

Research support (all sprints): J. Azuela (PM/lead researcher), H. Gili and D. Parcia (requirements research, testing, documentation).

### 3.4.6.1 Sprint Burndown Chart

Story points were estimated per sprint using a modified Fibonacci scale (1, 2, 3, 5, 8). Sprint 3 (booking + AI) is shown below as the representative burndown; similar charts were maintained for Sprints 1–5 during development.

Sprint 3 summary: 34 story points · 7-day sprint · Team velocity ≈ 34 points/sprint

Table 10. Sprint 3 Burndown Data (Story Points Remaining)

| Day | Date (approx.) | Ideal Remaining | Actual Remaining | Notes |
| --- | --- | --- | --- | --- |
| 0 | Jan 9 | 34 | 34 | Sprint planning — S3_1 to S3_5 committed |
| 1 | Jan 10 | 29 | 32 | Booking form scaffold; AI API design |
| 2 | Jan 11 | 24 | 28 | F21 validation; conflict API wired |
| 3 | Jan 12 | 19 | 22 | F22/F23 integrated on book page |
| 4 | Jan 13 | 14 | 14 | F24 auto-approval complete |
| 5 | Jan 14 | 9 | 8 | F25 tabbed approvals started |
| 6 | Jan 15 | 5 | 4 | F26 decision actions |
| 7 | Jan 16 | 0 | 0 | F27/F28 done; sprint review |

Figure — Sprint 3 Burndown Chart (insert in Word)

xychart-beta
    title "Sprint 3 Burndown — Booking & AI (34 pts)"
    x-axis ["Day 0", "Day 1", "Day 2", "Day 3", "Day 4", "Day 5", "Day 6", "Day 7"]
    y-axis "Story Points Remaining" 0 --> 35
    line "Ideal" [34, 29, 24, 19, 14, 9, 5, 0]
    line "Actual" [34, 32, 28, 22, 14, 8, 4, 0]

Alternative for Word: Export the chart from Mermaid Live Editor as PNG, or recreate in Excel using Table 10 values (Ideal = linear burn from 34 to 0; Actual = column “Actual Remaining”).

Sprint point totals (reference):

| Sprint | Theme | Committed Points | Status |
| --- | --- | --- | --- |
| Sprint 1 | Auth & security | 28 | Completed |
| Sprint 2 | Profile, facilities, public UI | 30 | Completed |
| Sprint 3 | Booking, AI, approvals | 34 | Completed |
| Sprint 4 | Attendance, calendar, reports | 32 | Completed |
| Sprint 5 | Integrations, compliance, polish | 36 | Completed |

## 3.4.7 Increment

Each sprint produced a potentially shippable increment deployed to staging and, after review, to production (cprf.infragovservices.com).

Table 11. Increment

| Sprint No. | Increment / Feature Delivered | User Story / Backlog Reference | Definition of Done (DoD) Criteria | Status | Remarks |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Secure registration and login module | F1–F3, F5–F6, IS-1–IS-4, IS-9 | Code complete · Unit/smoke tested · DB integrated · Docs updated | Done | OTP login and lockout working |
| Sprint 1 | Password reset and session hardening | F5, IS-2, IS-9 | Token emails delivered · CSRF on forms · Session timeout verified | Done | Production email via SMTP |
| Sprint 2 | User profile and document handling | F7, IS-6, F8 | Upload validation · Secure paths · Admin review in User Management | Done | PDF/JPG/PNG/WebP supported |
| Sprint 2 | Public portal and facility management | F11–F16, UI-1, UI-6 | Public pages live · Facility CRUD · Geocoding on map | Done | OpenStreetMap integration |
| Sprint 2 | ID verification queue | F9 | Dedicated tab · Verify/redo workflow · Booking gate for unverified IDs | Done | July 2026 enhancement |
| Sprint 3 | Booking and AI scheduling core | F21–F24, F30 | Book form · Conflict API · Recommendations · Auto-approval | Done | Python ML + PHP orchestration |
| Sprint 3 | Staff approval operations | F25–F28 | Pending/approved tabs · Approve/deny/modify · My Reservations | Done | Tabbed UI redesign Jul 2026 |
| Sprint 4 | Attendance and occupancy | F31–F33 | Manual + QR check-in · Occupancy strip · No-show violations | Done | Facility QR posters |
| Sprint 4 | Calendar and analytics | F35–F36, ASA-1–ASA-4 | iCal export · Reports CSV/PDF · Dashboard KPI filters | Done | Print-ready CSS |
| Sprint 4 | Smart Scheduler & chatbot foundation | F34 | Smart Scheduler page · ML risk/purpose · Chat widget shell | Done | Gemini added Sprint 5 |
| Sprint 5 | CIMM integration & auto-announcements | F37, INT-1, INT-4 | CIMM pull sync · Blackout sync · Gemini public posts | Done | Cron + manual sync page |
| Sprint 5 | CPRF blackout Gemini announcements | F17, INT-4 | Manual blackout → auto public notification with facility photo | Done | July 2026 |
| Sprint 5 | Infrastructure & UMAN dashboards | F38, INT-2, INT-3 | Integration pages · Brgy Culiat scope · UMAN asset assign | Connected† | Auto-blackout not implemented |
| Sprint 5 | Compliance and admin tools | F39, F10, EA-1 | Audit export · Document archival cron · DPA JSON export | Done | Retention policy in admin |
| Sprint 5 | Notifications and communications | F40, INT-6 | In-app · Email · SMS opt-in · Booking reminders cron | Done | Brevo/SMTP configurable |
| Sprint 5 | Optional PayMongo payments | INT-5 | Checkout session · Webhook · Payment return page | Optional | Disabled by default |
| — | Filipino UI / PWA / health endpoint | UI-11, UI-12, EA-6, INT-8 | — | Planned | Future backlog |

† Infrastructure: connected for barangay-scoped construction reports per thesis scope; technical connection mechanics not expanded in this chapter.

## Appendix — Traceability Quick Reference

| Thesis ID | Maps to User Story Doc |
| --- | --- |
| F1–F10 | US-1.x, US-2.x (USER_STORIES_AND_BACKLOG_COMPLETE.md) |
| F11–F20 | US-3.x, US-4.x |
| F21–F30 | US-5.x |
| F31–F40 | US-6.x – US-11.x |
| IS-1–IS-10 | Security epic + config/security.php |
| INT-1–INT-8 | US-10.x integrations |
| ASA-1–ASA-8 | US-7.x, US-8.x analytics |
| EA-1–EA-6 | US-8.x, US-11.x compliance |

End of §3.4 Scrum Artifacts — ready for Word paste.